## Read me
WOBBLE × the digital engine — 90-Day Roadmap Tracker
Companion to the 90-Day Marketing Roadmap PDF (November 2026 to January 2027). Portfolio sample: WOBBLE is an invented brand and every figure is illustrative.
How to use it
• The '12-week tracker' tab lists every action from the roadmap, in order, with its owner, dates, measure and the roadmap page it comes from.
• You edit only the YELLOW cells: Status (pick from the dropdown) and Notes. Everything else is the plan as written.
• Example of the expected format: row 4 of the tracker is filled in as an example — status 'In progress', a one-line dated note.
• The 'Fact ledger' tab records what was supplied, what we verified, and what is still an assumption, with a checked-on date per line. Add rows as facts arrive.
the digital engine · thedigitalengine.ie/grow · hello@thedigitalengine.ie

## 12-week tracker
WOBBLE — 12-week action tracker · Nov 2026 to Jan 2027 (portfolio sample)
Fortnight | Dates | Action | Owner | Status | Measure | Roadmap pg | Notes
W1–2 | Mon 2 – Sun 15 Nov | Email sign-up live, with the QR generated for counter cards | Founder A | In progress | Sign-ups per week visible in the platform | 3 Nov: QR tested on two phones; platform set up on the free tier
W1–2 | Mon 2 – Sun 15 Nov | Baseline numbers recorded: stockists, followers, list size | Founder B |  | Row completed in Fact ledger | 4
W1–2 | Mon 2 – Sun 15 Nov | Stockist kit designed: shelf strip, counter card, poster | Both |  | Kit approved by both founders | 4
W3–4 | Mon 16 – Sun 29 Nov | Kit printed: 28 sets plus 12 spares | Founder A |  | Kits in hand by Wed 18 Nov | 4
W3–4 | Mon 16 – Sun 29 Nov | Kits delivered — ten biggest stockists in person | Both |  | 28 of 28 delivered; displays photographed | 4
W3–4 | Mon 16 – Sun 29 Nov | Display photos reposted same day, shops tagged | Founder B |  | Photo bank ready for weeks 7–8 | 4
W5–6 | Mon 30 Nov – Sun 13 Dec | 'Bring The Fun One' fortnight: 6 posts, six-pack focus | Founder B |  | 6 posts out; list pitched in every caption | 4
W5–6 | Mon 30 Nov – Sun 13 Dec | New-stockist pitches continue: 10 per week | Founder A |  | Replies logged; running stockist count | 4
W5–6 | Mon 30 Nov – Sun 13 Dec | January displays agreed in writing with 15 stockists | Founder A |  | 15 written confirmations by Fri 11 Dec | 4, 7
W7–8 | Mon 14 – Sun 27 Dec | Shop-a-day advent stories to Christmas week | Founder B |  | One stockist per day; reposts counted | 4
W7–8 | Mon 14 – Sun 27 Dec | Every January asset delivered to shops | Founder A |  | All delivered by Fri 18 Dec | 4, 7
W9–10 | Mon 28 Dec – Sun 10 Jan | Displays up and photographed | Both |  | 15 displays confirmed by Sat 2 Jan | 4, 7
W9–10 | Mon 28 Dec – Sun 10 Jan | Launch email to the list | Founder B |  | Sent Mon 4 Jan, 8am; opens and clicks noted | 4, 6
W9–10 | Mon 28 Dec – Sun 10 Jan | Launch-week captions posted (3, as written) | Founder B |  | 3 posted in week of 4 Jan | 4, 6
W11–12 | Mon 11 – Sun 24 Jan | Weekly display photos and list counts collected | Founder B |  | Sign-ups per stockist tracked weekly | 7
W11–12 | Mon 11 – Sun 24 Jan | Quarter review against this tracker | Both |  | Done in week of Mon 18 Jan | 4
W11–12 | Mon 11 – Sun 24 Jan | Spring targets set from the actual numbers | Both |  | Three targets written down | 4
|  | Actions marked Done: |  | 0 of 17
Yellow cells are yours to edit (Status and Notes). All dates verified against the 2026–27 calendar.

## Fact ledger
WOBBLE — fact ledger (portfolio sample; every line illustrative)
Status | Fact | Source | Checked on
Supplied | 28 independent stockists; roughly 60% of volume through the biggest ten | Founders, discovery call | 3 Nov 2026
Supplied | No email list exists yet; Instagram at ~1,900 followers | Founders, discovery call | 3 Nov 2026
Verified | Hazy Days Soda and KindBubbles stocked in 4 of WOBBLE's ten biggest shops | Shelf photos on file | 5 Nov 2026
Assumption | Stockists will display point-of-sale material if it's funny enough to want on the counter | Tested by the week-3 kit | —
Assumption | Dry January buyers will travel to a named stockist from the online list | Tested by the launch email | —
To confirm | Printer lead time for the kit (needed in hand by 18 Nov) | Quote requested | —
Add rows as facts arrive. Nothing marked 'Assumption' or 'To confirm' may appear in a deliverable as fact.